## Current List
CS# | Store # | 5 Digit Store | Div | Reg | Dist | Cluster | Address | City | State | Zip | Store Type | PM/SPM | Layout Validation Status | MV or Store Labor? | Merchandising Hours | GC | MV | Unit Configuration | MSD | CSD | Notes
190032 | 10880 | 10880 | 07 | 37 | 03 | 149 | 8580 N. MACARTHUR BLVD | IRVING | TX | 75063 | Freestanding | Soto; Joseph | Approved | MV | 64 | Core CMCI | Channel Partners | 3 | 2026-10-05
190020 | 10996 | 10996 | 07 | 33 | 01 | 145 | 9663 W. FM 1097 RD. | WILLIS | TX | 77318 | Freestanding | Cathey; Chris C. | Approved | MV | 32 | Core CMCI | Pivotal | 3 | 2026-10-12
189469 | 6893 | 06893 | 07 | 35 | 02 | 147 | 3569 FAR WEST BLVD. | AUSTIN | TX | 78731 | Strip Shopping Center | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-12
190027 | 10691 | 10691 | 07 | 35 | 01 | 147 | 302 GATEWAY NORTH | MARBLE FALLS | TX | 78654 | Freestanding | Soto; Joseph | Approved | MV | 44 | Core CMCI | Merchco | 3 | 2026-10-12
190030 | 10633 | 10633 | 07 | 35 | 04 | 148 | 3502 SE MILITARY DR. | SAN ANTONIO | TX | 78223 | Freestanding | Soto; Joseph | Approved | MV | 6 | Core CMCI | Pivotal | 3 | 2026-10-12
189985 | 10324 | 10324 | 07 | 36 | 05 | 149 | 6420 GASTON AVE. | DALLAS | TX | 75214 | Convenience | Soto; Joseph | Approved | Store Labor | 22 | Core CMCI | N/A | 4 | 2026-10-12
190033 | 10642 | 10642 | 07 | 37 | 05 | 149 | 1101 FM 2181 | CORINTH | TX | 76210 | Freestanding | Soto; Joseph | Approved | MV | 34 | Core CMCI | Channel Partners | 3 | 2026-10-12
189518 | 7092 | 07092 | 07 | 33 | 02 | 145 | 110 W. 20TH ST. | HOUSTON | TX | 77008 | Freestanding | Cathey; Chris C. | Approved | MV | 70 | Core CMCI | Pivotal | 3 | 2026-10-19
189171 | 1996 | 01996 | 07 | 34 | 01 | 146 | 24950 FRANZ RD. | KATY | TX | 77493 | Freestanding | Soto; Joseph | Approved | Store Labor | 38 | Core CMCI | N/A | 3 | 2026-10-19
190024 | 10671 | 10671 | 07 | 34 | 04 | 146 | 10420 FM 1464 | RICHMOND | TX | 77407 | Freestanding | Soto; Joseph | Approved | Store Labor | 8 | Core CMCI | N/A | 3 | 2026-10-19
190025 | 10637 | 10637 | 07 | 34 | 04 | 147 | 6750 READING ROAD | ROSENBERG | TX | 77471 | Freestanding | Soto; Joseph | Approved | Store Labor | 14 | Core CMCI | N/A | 3 | 2026-10-19
190026 | 10875 | 10875 | 07 | 35 | 01 | 147 | 3000 RM 1431 | ROUND ROCK | TX | 78681 | Freestanding | Soto; Joseph | Approved | Store Labor | 10 | Core CMCI | N/A | 3 | 2026-10-19
190029 | 10750 | 10750 | 07 | 35 | 04 | 148 | 9050 FM 1560 N | SAN ANTONIO | TX | 78254 | Freestanding | Soto; Joseph | Approved | MV | 40 | Core CMCI | Pivotal | 3 | 2026-10-19
190028 | 10947 | 10947 | 07 | 35 | 03 | 148 | 1910 STATE HIGHWAY 46 W | NEW BRAUNFELS | TX | 78132 | Freestanding | Soto; Joseph | Approved | Store Labor | 6 | Core CMCI | N/A | 3 | 2026-10-19
189620 | 8345 | 08345 | 07 | 37 | 02 | 149 | 5195 LAKE RIDGE PKWY. | GRAND PRAIRIE | TX | 75052 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 2 - Right Hinge | 2026-10-19
189473 | 6865 | 06865 | 07 | 37 | 03 | 149 | 1099 W. MAIN ST | LEWISVILLE | TX | 75067 | Freestanding | Soto; Joseph | Approved | MV | 52 | Core CMCI | Channel Partners | 4 | 2026-10-19
189419 | 5839 | 05839 | 07 | 33 | 01 | 145 | 8960 BARKER CYPRESS RD. | CYPRESS | TX | 77433 | Freestanding | Cathey; Chris C. | Approved | MV | 10 | Core CMCI | Pivotal | 3 | 2026-10-26
189977 | 10594 | 10594 | 07 | 32 | 03 | 145 | 500 N. CARROLLTON AVE. | NEW ORLEANS | LA | 70119 | Freestanding | Cathey; Chris C. | Approved | Store Labor | 34 | Core CMCI | N/A | 3 | 2026-10-26
189422 | 5651 | 05651 | 07 | 34 | 02 | 146 | 1602 EAST HIGHWAY 83 | WESLACO | TX | 78596 | Freestanding | Soto; Joseph | Approved | MV | 52 | Core CMCI | Merchco | 4 | 2026-10-26
189421 | 5884 | 05884 | 07 | 34 | 01 | 146 | 12260 BELLAIRE BLVD. | HOUSTON | TX | 77072 | Freestanding | Soto; Joseph | Approved | Store Labor | 30 | Core CMCI | N/A | 3 | 2026-10-26
189523 | 7805 | 07805 | 07 | 34 | 04 | 147 | 5757 NEW TERRITORY BLVD | SUGAR LAND | TX | 77479 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-26
189425 | 5776 | 05776 | 07 | 35 | 02 | 147 | 105 WONDERWORLD DRIVE | SAN MARCOS | TX | 78666 | Freestanding Pad | Soto; Joseph | Approved | MV | 74 | Core CMCI | Merchco | 3 | 2026-10-26
189074 | 1430 | 01430 | 07 | 35 | 02 | 148 | 2101 S. LAMAR BLVD., UNIT B | AUSTIN | TX | 78704 | Strip Shopping Center | Soto; Joseph | Approved | MV | 40 | Core CMCI | Pivotal | 3 | 2026-10-26
189470 | 6822 | 06822 | 07 | 35 | 02 | 148 | 5256 BURNET RD STE B | AUSTIN | TX | 78756 | Freestanding | Soto; Joseph | Approved | Store Labor | 12 | Core CMCI | N/A | 3 | 2026-10-26
189281 | 3187 | 03187 | 07 | 37 | 03 | 149 | 1000 E. SANDY LAKE RD. | COPPELL | TX | 75019 | Freestanding Pad | Soto; Joseph | Approved | MV | 46 | Core CMCI | Channel Partners | 3 | 2026-10-26
189528 | 7787 | 07787 | 07 | 37 | 03 | 149 | 2220 CROSS TIMBERS RD | FLOWER MOUND | TX | 75028 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-26
189516 | 7448 | 07448 | 07 | 33 | 01 | 145 | 815 W. MAIN ST. | TOMBALL | TX | 77375 | Freestanding | Cathey; Chris C. | Approved | MV | 36 | Core CMCI | Pivotal | 3 | 2026-11-02
190021 | 10664 | 10664 | 07 | 33 | 01 | 145 | 2180 WOODFOREST PARKWAY N. | MONTGOMERY | TX | 77316 | Freestanding Pad | Cathey; Chris C. | Approved | Store Labor | 34 | Core CMCI | N/A | 3 | 2026-11-02
189926 | 10107 | 10107 | 07 | 34 | 02 | 146 | 2300 N CONWAY AVE. | MISSION | TX | 78574 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-02
189978 | 10405 | 10405 | 07 | 34 | 02 | 146 | 103 W. MONTE CRISTO RD. | EDINBURG | TX | 78541 | Freestanding | Soto; Joseph | Approved | MV | 62 | Core CMCI | Merchco | 4 | 2026-11-02
189279 | 3693 | 03693 | 07 | 34 | 04 | 147 | 7950 S. GESSNER RD. | HOUSTON | TX | 77036 | Freestanding | Soto; Joseph | Approved | MV | 56 | Core CMCI | Merchco | 3 | 2026-11-02
189322 | 4474 | 04474 | 07 | 34 | 04 | 147 | 2781 DULLES AVE. | MISSOURI CITY | TX | 77459 | Freestanding | Soto; Joseph | Approved | MV | 66 | Core CMCI | Merchco | 3 | 2026-11-02
189984 | 10595 | 10595 | 07 | 35 | 03 | 148 | 200 CIBOLO VALLEY DR. | CIBOLO | TX | 78108 | Freestanding | Soto; Joseph | Approved | Store Labor | 36 | Core CMCI | N/A | 4 | 2026-11-02
189526 | 7307 | 07307 | 07 | 35 | 04 | 148 | 2018 CULEBRA RD. | SAN ANTONIO | TX | 78201 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-02
189474 | 6960 | 06960 | 07 | 37 | 04 | 149 | 2142 N JOSEY LN | CARROLLTON | TX | 75006 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-11-02
189529 | 7804 | 07804 | 07 | 37 | 04 | 149 | 6401 W PARKER RD | PLANO | TX | 75093 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-11-02
189519 | 7476 | 07476 | 07 | 33 | 02 | 145 | 5401 WASHINGTON AVE | HOUSTON | TX | 77007 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-09
188919 | 248 | 00248 | 07 | 34 | 02 | 146 | 2121 W. TRENTON RD. | EDINBURG | TX | 78539 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189979 | 10350 | 10350 | 07 | 34 | 03 | 146 | 4523 L J PARKWAY | SUGAR LAND | TX | 77479 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189927 | 10177 | 10177 | 07 | 34 | 04 | 147 | 2720 FM 1463 | KATY | TX | 77494 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189424 | 5972 | 05972 | 07 | 34 | 04 | 147 | 5305 AVENUE I | ROSENBERG | TX | 77471 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
190031 | 10635 | 10635 | 07 | 36 | 01 | 148 | 476 W. 1-30 | ROYSE CITY | TX | 75189 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-09
189471 | 6655 | 06655 | 07 | 36 | 03 | 148 | 1569 11TH ST | HUNTSVILLE | TX | 77340 | Freestanding | Soto; Joseph | Approved | MV | 56 | Core CMCI | Pivotal | 3 | 2026-11-09
189426 | 5799 | 05799 | 07 | 37 | 05 | 149 | 6301 EL DORADO PKWY. | MCKINNEY | TX | 75070 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-09
189986 | 10271 | 10271 | 07 | 37 | 05 | 149 | 1510 W. HICKORY ST. | DENTON | TX | 76201 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-09
189521 | 7475 | 07475 | 07 | 33 | 03 | 145 | 1350 KINGWOOD DR | KINGWOOD | TX | 77339 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
190022 | 11067 | 11067 | 07 | 33 | 04 | 145 | 2735 SIENNA PARKWAY | MISSOURI CITY | TX | 77459 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
189190 | 2328 | 02328 | 07 | 34 | 03 | 146 | 3205 S. ALAMEDA ST. | CORPUS CHRISTI | TX | 78404 | Freestanding Pad | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189423 | 5519 | 05519 | 07 | 34 | 03 | 146 | 1295 EAST LEAGUE CITY PKWY. | LEAGUE CITY | TX | 77573 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189982 | 10585 | 10585 | 07 | 35 | 01 | 147 | 3300 W. STAN SCHLUETER LOOP | KILLEEN | TX | 76549 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189928 | 10221 | 10221 | 07 | 35 | 01 | 147 | 2502 TRIMMIER RD. | KILLEEN | TX | 76542 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189983 | 10579 | 10579 | 07 | 35 | 03 | 148 | 4600 BROADWAY ST. | ALAMO HEIGHTS | TX | 78209 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
189472 | 6965 | 06965 | 07 | 36 | 04 | 148 | 7203 SKILLMAN ST. | DALLAS | TX | 75231 | Freestanding Pad | Soto; Joseph | Not Validated Yet | MV |  | Core CMCI | Pivotal |  | 2026-11-16
189987 | 10523 | 10523 | 07 | 37 | 05 | 149 | 270 STONEBROOK PKWY. | FRISCO | TX | 75036 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-16
189427 | 5952 | 05952 | 07 | 37 | 05 | 149 | 2313 W. UNIVERSITY AVE. | MCKINNEY | TX | 75071 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-16
189522 | 7120 | 07120 | 07 | 33 | 04 | 145 | 11600 SHADOW CREEK PKWY. | PEARLAND | TX | 77584 | Freestanding Pad | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189420 | 6000 | 06000 | 07 | 33 | 04 | 145 | 4101 FAIRMONT PKWY., | PASADENA | TX | 77504 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189980 | 10544 | 10544 | 07 | 34 | 04 | 146 | 5902 FM 1463 RD. | KATY | TX | 77494 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
190023 | 10604 | 10604 | 07 | 33 | 04 | 146 | 4489 COUNTY ROAD 94 | MANVEL | TX | 77578 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
189024 | 928 | 00928 | 07 | 35 | 01 | 147 | 800 WEST OLD SETTLERS BLVD | ROUND ROCK | TX | 78681 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
188921 | 357 | 00357 | 07 | 35 | 01 | 147 | 1701 E. PARMER LN. | AUSTIN | TX | 78754 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
189524 | 7808 | 07808 | 07 | 35 | 03 | 148 | 4805 MEDICAL DR | SAN ANTONIO | TX | 78229 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189525 | 7784 | 07784 | 07 | 35 | 03 | 148 | 110 S KING ST | SEGUIN | TX | 78155 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189530 | 7562 | 07562 | 07 | 37 | 05 | 149 | 9075 LEGACY DR. | FRISCO | TX | 75033 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-30
189116 | 1543 | 01543 | 07 | 38 | 01 | 149 | 7301 HILLSIDE RD. | AMARILLO | TX | 79119 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-30

## Rejected Candidates
Store # | 5 Digit Store | CS# | Div | Reg | Dist | Cluster | Address | City | State | Zip | Store Type | PM/SPM | Layout Validation Status | MV or Store Labor? | Merchandising Hours | Unit Configuration | MSD | CSD
9481 | 09481 | 189774 | 09 | 89 | 02 | 169 | 12444 BEACH BOULEVARD | STANTON | CA | 90680 | Freestanding | Winkler; Jacob S | Rejected |  |  |  | 2026-11-09
915 | 00915 | 188989 | 01 | 02 | 03 | 105 | 19 DODGE ST. | BEVERLY | MA | 01915 | Freestanding Pad | Wheeler; Nicolas | Rejected |  |  |  | 2026-10-05
224 | 00224 | 188874 | 01 | 02 | 03 | 105 | 650 MAIN STREET | READING | MA | 01867 | Downtown | Wheeler; Nicolas | Rejected |  |  |  | 2026-10-19
860 | 00860 | 188992 | 01 | 03 | 02 | 106 | 6 POST OFFICE SQ | HARWICHPORT | MA | 02646 | Convenience | Wheeler; Nicolas | Rejected |  |  |  | 2026-11-30
1213 | 01213 | 189038 | 01 | 04 | 03 | 109 | 94 PARK STREET | NEW CANAAN | CT | 06840 | Downtown | Charlotinambrose; Mildred | Rejected |  |  |  | 2026-11-09
11060 | 11060 | 190007 | 02 | 06 | 05 | 115 | 1-50 50TH AVE | LONG ISLAND CITY | NY | 11101 | Downtown | Kaegi; Jacqueline | Rejected |  |  |  | 2026-11-30
1833 | 01833 | 189103 | 02 | 17 | 02 | 120 | 4238 WILSON BLVD/BALLSTON COMMONS #1831 | ARLINGTON | VA | 22203 | Regional Mall | Meath; Lori A. | Rejected |  |  |  | 2026-10-19
8088 | 08088 | 189571 | 03 | 58 | 02 | 130 | 2100 W. STADIUM BLVD. | ANN ARBOR | MI | 48103 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
1389 | 01389 | 189072 | 04 | 19 | 02 | 140 | 2912 CHAIN BRIDGE ROAD | OAKTON | VA | 22124 | Strip Shopping Center | Meath; Lori A. | Rejected |  |  |  | 2026-10-12
3705 | 03705 | 189277 | 05 | 83 | 03 | 144 | 10701 NW 41ST ST | DORAL | FL | 33178 | Freestanding | townsend; kevin | Rejected |  |  |  | 2026-11-30
5443 | 05443 | 189374 | 07 | 32 | 02 | 145 | 1920 KALISTE SALOOM | LAFAYETTE | LA | 70508 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
7435 | 07435 | 189520 | 07 | 33 | 03 | 145 | 23865 FM 1314 RD. | PORTER | TX | 77365 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-11-09
9108 | 09108 | 189671 | 09 | 87 | 04 | 165 | 1655 S. CENTRE CITY PKWY. | ESCONDIDO | CA | 92025 | Freestanding Pad | Foster; Ryan | Rejected |  |  |  | 2026-10-26
9614 | 09614 | 189791 | 09 | 90 | 02 | 172 | 1122 EAST BROADWAY | GLENDALE | CA | 91205 | Convenience | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
9787 | 09787 | 189839 | 09 | 90 | 02 | 172 | 3943 SAN FERNANDO RD. | GLENDALE | CA | 91204 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-26
2981 | 02981 | 189240 | 12 | 61 | 04 | 183 | 1201 N. STATE ST. | CHICAGO | IL | 60610 | Freestanding | O Rourke; Jessica A | Rejected |  |  |  | 2026-11-16
2054 | 02054 | 189131 | 01 | 03 | 04 | 107 | 136 NAHATAN ST. | NORWOOD | MA | 02062 | Strip Shopping Center | Manning; Robert | Rejected |  |  |  | 2026-10-26
300 | 00300 | 188892 | 02 | 06 | 01 | 113 | 725 SAW MILL RIVER RD, ARDSLEY S/C | ARDSLEY | NY | 10502 | Convenience | Kaegi; Jacqueline | Rejected |  |  |  | 2026-10-19
1231 | 01231 | 189043 | 02 | 06 | 01 | 113 | 807 WHITE PLAINS RD. | SCARSDALE | NY | 10583 | Freestanding | Kaegi; Jacqueline | Rejected |  |  |  | 2026-10-26
2225 | 02225 | 189142 | 02 | 08 | 01 | 115 | 232 SMITHTOWN BOULEVARD | NESCONSET | NY | 11767 | Freestanding Pad | Kaegi; Jacqueline | Rejected |  |  |  | 2026-11-02
4323 | 04323 | 189312 | 03 | 31 | 01 | 127 | 10050 WOODLAND RD. | LENEXA | KS | 66220 | Freestanding Pad | O Rourke; Jessica A | Rejected |  |  |  | 2026-10-26
7859 | 07859 | 189588 | 08 | 30 | 04 | 151 | 6370 N. CAMPBELL AVE., #120 | TUCSON | AZ | 85718 | Convenience | Sotelo; Rolly | Rejected |  |  |  | 2026-11-30
9498 | 09498 | 189756 | 09 | 52 | 01 | 157 | 1800 SARATOGA AVE. | SAN JOSE | CA | 95129 | Freestanding Pad | Morgan; Marina L | Rejected |  |  |  | 2026-10-26
7774 | 07774 | 189535 | 09 | 52 | 01 | 157 | 850 CALIFORNIA ST | MOUNTAIN VIEW | CA | 94041 | Downtown | Morgan; Marina L | Rejected |  |  |  | 2026-10-26
9148 | 09148 | 189668 | 09 | 87 | 03 | 164 | 313 WASHINGTON ST. | SAN DIEGO | CA | 92103 | Freestanding | Foster; Ryan | Rejected |  |  |  | 2026-11-02
9591 | 09591 | 189768 | 09 | 88 | 01 | 166 | 30842 S PACIFIC COAST | LAGUNA BEACH | CA | 92651 | Strip Shopping Center | Fitzpatrick; John T | Rejected |  |  |  | 2026-10-26
8837 | 08837 | 189638 | 09 | 90 | 03 | 173 | 222 N. MARKET ST. | INGLEWOOD | CA | 90301 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
9698 | 09698 | 189824 | 09 | 88 | 02 | 168 | 100 W. FOOTHILL BLVD. | UPLAND | CA | 91786 | Freestanding Pad | Winkler; Jacob S | Rejected |  |  |  | 2026-10-05
8895 | 08895 | 189691 | 09 | 88 | 02 | 170 | 775 E. FOOTHILL BOULEVARD | POMONA | CA | 91767 | Strip Shopping Center | Winkler; Jacob S | Rejected |  |  |  | 2026-11-16
189064 | 1315 | 01315 | 04 | 14 | 04 | 138 | 1101 SOUTHWEST END BLVD. | QUAKERTOWN | PA | 18951 | Freestanding | Santalucia; Dawn | Rejected |  |  |  | 2026-10-26
189566 | 8016 | 08016 | 03 | 57 | 05 | 129 | 40925 GARFIELD ROAD | CLINTON TOWNSHIP | MI | 48038 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
189572 | 8089 | 08089 | 03 | 58 | 02 | 130 | 935 S. MAIN ST. | CHELSEA | MI | 48118 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
189073 | 1411 | 01411 | 04 | 19 | 02 | 140 | 8124 ARLINGTON BLVD, YORKTOWN CTR | FALLS CHURCH | VA | 22042 | Strip Shopping Center | Meath; Lori A. | Rejected |  |  |  | 2026-11-02
189198 | 3154 | 03154 | 01 | 05 | 01 | 110 | 59 MAIN STREET | WARWICK | NY | 10990 | Freestanding | Messer; Laura R | Rejected |  |  |  | 2026-11-09
189041 | 1414 | 01414 | 01 | 07 | 01 | 112 | 1195 OAKLAWN AVENUE | CRANSTON | RI | 02920 | Freestanding Pad | Messer; Laura R | Rejected |  |  |  | 2026-11-09
189573 | 8216 | 08216 | 03 | 58 | 02 | 130 | 1700 SOUTH INDUSTRIAL HIGHWAY | ANN ARBOR | MI | 48104 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-09
189268 | 3218 | 03218 | 05 | 41 | 01 | 142 | 10200 SEMINOLE BLVD | SEMINOLE | FL | 33778 | Freestanding | townsend; kevin | Rejected |  |  |  | 2026-11-09
189625 | 8420 | 08420 | 08 | 30 | 04 | 151 | 7740 N CORTARO RD | TUCSON | AZ | 85743 | Freestanding | Sotelo; Rolly | Rejected |  |  |  | 2026-11-09
189406 | 5741 | 05741 | 03 | 58 | 01 | 129 | 7488 VILLAGE CENTER DR. | WHITMORE LAKE | MI | 48189 | Freestanding Pad | Clark; Josh D. | Rejected |  |  |  | 2026-11-30
188962 | 660 | 00660 | 04 | 13 | 01 | 135 | 9875 BUSTLETON AVENUE | PHILADELPHIA | PA | 19115 | Freestanding Pad | Santalucia; Dawn | Rejected |  |  |  | 2026-10-26
189840 | 9784 | 09784 | 09 | 90 | 02 | 172 | 1030 COLORADO BLVD. | EAGLE ROCK | CA | 90041 | Freestanding | Cathey; Chris C. | Approved | MV | 60 | 2 | 2026-10-19

## Assumptions
Logistics Plan - Assumptions (edit yellow cells; plan recalculates)
Global inputs
Default units per store when config is blank/TBD | 3 | Most common configuration among the 35 validated stores (29 are 3-unit)
Delivery buffer before MSD (business days) | 3 | Units on site, checked and staged before install starts. ASSUMPTION - confirm with vendor/CVS
Install days per store (crew-days) | 1 | ASSUMPTION - confirm actual install duration per unit config
Transit time from vendor/staging point to region (business days)
Region | Transit days | Note
DFW | 2 | PLACEHOLDER - update once ship-from point is known
Houston | 2 | PLACEHOLDER
Austin / Central | 2 | PLACEHOLDER
San Antonio | 2 | PLACEHOLDER
South TX | 3 | PLACEHOLDER - RGV / Corpus are long hauls
Outlier | 4 | PLACEHOLDER - Amarillo and New Orleans are out of the way
Definitions used
MSD = date install window opens per the store list. CSD = MSD + 7 days (existing formula in the list).
Deliver-by = MSD less the delivery buffer (business days). Ship-by = Deliver-by less regional transit days.
Units come from the Unit Configuration column; stores not yet validated have none, so the default above is used and flagged TBD.
Regions are grouped by metro so one crew/truck run covers a cluster. Killeen is grouped with Austin / Central.
Plan tab pulls MSD, labor and status live from Current List by CS#.

## Logistics Plan
Core CMCI - Consultation Room Logistics Plan
Sorted by region, then MSD. Dates and units are formulas driven by the Assumptions tab and Current List.
Region | CS# | Store # | City | State | Zip | Store Type | Labor (MV / Store) | MV Vendor | Layout Status | Config (raw) | Units | Config | MSD | Deliver-by | Ship-by | Ship week of (Mon) | CSD | Flags
DFW | 190032 | 10880 | Irving | TX | 75063
DFW | 190033 | 10642 | Corinth | TX | 76210
DFW | 189985 | 10324 | Dallas | TX | 75214
DFW | 189620 | 8345 | Grand Prairie | TX | 75052
DFW | 189473 | 6865 | Lewisville | TX | 75067
DFW | 189281 | 3187 | Coppell | TX | 75019
DFW | 189528 | 7787 | Flower Mound | TX | 75028
DFW | 189474 | 6960 | Carrollton | TX | 75006
DFW | 189529 | 7804 | Plano | TX | 75093
DFW | 189986 | 10271 | Denton | TX | 76201
DFW | 189426 | 5799 | Mckinney | TX | 75070
DFW | 190031 | 10635 | Royse City | TX | 75189
DFW | 189472 | 6965 | Dallas | TX | 75231
DFW | 189987 | 10523 | Frisco | TX | 75036
DFW | 189427 | 5952 | Mckinney | TX | 75071
DFW | 189530 | 7562 | Frisco | TX | 75033
Houston | 190020 | 10996 | Willis | TX | 77318
Houston | 189518 | 7092 | Houston | TX | 77008
Houston | 189171 | 1996 | Katy | TX | 77493
Houston | 190024 | 10671 | Richmond | TX | 77407
Houston | 190025 | 10637 | Rosenberg | TX | 77471
Houston | 189419 | 5839 | Cypress | TX | 77433
Houston | 189421 | 5884 | Houston | TX | 77072
Houston | 189523 | 7805 | Sugar Land | TX | 77479
Houston | 189279 | 3693 | Houston | TX | 77036
Houston | 189322 | 4474 | Missouri City | TX | 77459
Houston | 190021 | 10664 | Montgomery | TX | 77316
Houston | 189516 | 7448 | Tomball | TX | 77375
Houston | 189519 | 7476 | Houston | TX | 77007
Houston | 189471 | 6655 | Huntsville | TX | 77340
Houston | 189927 | 10177 | Katy | TX | 77494
Houston | 189424 | 5972 | Rosenberg | TX | 77471
Houston | 189979 | 10350 | Sugar Land | TX | 77479
Houston | 189521 | 7475 | Kingwood | TX | 77339
Houston | 189423 | 5519 | League City | TX | 77573
Houston | 190022 | 11067 | Missouri City | TX | 77459
Houston | 189980 | 10544 | Katy | TX | 77494
Houston | 190023 | 10604 | Manvel | TX | 77578
Houston | 189420 | 6000 | Pasadena | TX | 77504
Houston | 189522 | 7120 | Pearland | TX | 77584
Austin / Central | 189469 | 6893 | Austin | TX | 78731
Austin / Central | 190027 | 10691 | Marble Falls | TX | 78654
Austin / Central | 190026 | 10875 | Round Rock | TX | 78681
Austin / Central | 189074 | 1430 | Austin | TX | 78704
Austin / Central | 189470 | 6822 | Austin | TX | 78756
Austin / Central | 189425 | 5776 | San Marcos | TX | 78666
Austin / Central | 189928 | 10221 | Killeen | TX | 76542
Austin / Central | 189982 | 10585 | Killeen | TX | 76549
Austin / Central | 188921 | 357 | Austin | TX | 78754
Austin / Central | 189024 | 928 | Round Rock | TX | 78681
San Antonio | 190030 | 10633 | San Antonio | TX | 78223
San Antonio | 190028 | 10947 | New Braunfels | TX | 78132
San Antonio | 190029 | 10750 | San Antonio | TX | 78254
San Antonio | 189984 | 10595 | Cibolo | TX | 78108
San Antonio | 189526 | 7307 | San Antonio | TX | 78201
San Antonio | 189983 | 10579 | Alamo Heights | TX | 78209
San Antonio | 189524 | 7808 | San Antonio | TX | 78229
San Antonio | 189525 | 7784 | Seguin | TX | 78155
South TX | 189422 | 5651 | Weslaco | TX | 78596
South TX | 189978 | 10405 | Edinburg | TX | 78541
South TX | 189926 | 10107 | Mission | TX | 78574
South TX | 188919 | 248 | Edinburg | TX | 78539
South TX | 189190 | 2328 | Corpus Christi | TX | 78404
Outlier | 189977 | 10594 | New Orleans | LA | 70119
Outlier | 189116 | 1543 | Amarillo | TX | 79119
Total
Formulas:
Deliver-by = WORKDAY([MSD],-Assumptions!$B5)
Ship-by = WORKDAY([Deliver-by],-VLOOKUP([Region],Assumptions!$A11:B16,2,FALSE))

## Region Summary
Region x MSD week: stores and units
Stores
Region | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-30 | Total
DFW
Houston
Austin / Central
San Antonio
South TX
Outlier
Total
Units (default used where config TBD)
Region | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-30 | Total
DFW
Houston
Austin / Central
San Antonio
South TX
Outlier
Total
Crew-days needed (stores x install days per store)
Peak week crew-days
Total crew-days
Crews needed at peak if each does 5 install days/week

## Map Data
Region | Store # | CS# | Address | City | State | Zip | Latitude | Longitude | MSD | Location basis
DFW | 10880 | 190032 | 8580 N. Macarthur Blvd | Irving | TX | 75063 | 32.9236 | -96.9553 | 2026-10-05 | Census address match
DFW | 10642 | 190033 | 1101 Fm 2181 | Corinth | TX | 76210 | 33.1328 | -97.0951 | 2026-10-12 | OSM CVS store match (FM 2181 = Teasley Ln)
DFW | 10324 | 189985 | 6420 Gaston Ave. | Dallas | TX | 75214 | 32.8148 | -96.7518 | 2026-10-12 | Census address match
DFW | 8345 | 189620 | 5195 Lake Ridge Pkwy. | Grand Prairie | TX | 75052 | 32.6481 | -97.0439 | 2026-10-19 | Census address match
DFW | 6865 | 189473 | 1099 W. Main St | Lewisville | TX | 75067 | 33.0422 | -97.0205 | 2026-10-19 | Census address match
DFW | 3187 | 189281 | 1000 E. Sandy Lake Rd. | Coppell | TX | 75019 | 32.9695 | -96.9586 | 2026-10-26 | Census address match
DFW | 7787 | 189528 | 2220 Cross Timbers Rd | Flower Mound | TX | 75028 | 33.0346 | -97.0625 | 2026-10-26 | Census address match
DFW | 6960 | 189474 | 2142 N Josey Ln | Carrollton | TX | 75006 | 32.9715 | -96.8898 | 2026-11-02 | Census address match
DFW | 7804 | 189529 | 6401 W Parker Rd | Plano | TX | 75093 | 33.0454 | -96.8396 | 2026-11-02 | Census address match
DFW | 10271 | 189986 | 1510 W. Hickory St. | Denton | TX | 76201 | 33.2147 | -97.1486 | 2026-11-09 | Census address match
DFW | 5799 | 189426 | 6301 El Dorado Pkwy. | Mckinney | TX | 75070 | 33.174 | -96.6991 | 2026-11-09 | Census address match
DFW | 10635 | 190031 | 476 W. 1-30 | Royse City | TX | 75189 | 32.9654 | -96.34 | 2026-11-09 | OSM CVS store match
DFW | 6965 | 189472 | 7203 Skillman St. | Dallas | TX | 75231 | 32.8787 | -96.7351 | 2026-11-16 | Census address match
DFW | 10523 | 189987 | 270 Stonebrook Pkwy. | Frisco | TX | 75036 | 33.1448 | -96.8901 | 2026-11-16 | Census address match
DFW | 5952 | 189427 | 2313 W. University Ave. | Mckinney | TX | 75071 | 33.2168 | -96.6445 | 2026-11-16 | Census address match
DFW | 7562 | 189530 | 9075 Legacy Dr. | Frisco | TX | 75033 | 33.1539 | -96.8481 | 2026-11-30 | Census address match
Houston | 10996 | 190020 | 9663 W. Fm 1097 Rd. | Willis | TX | 77318 | 30.4196 | -95.4981 | 2026-10-12 | Census address match
Houston | 7092 | 189518 | 110 W. 20Th St. | Houston | TX | 77008 | 29.8039 | -95.3981 | 2026-10-19 | Census address match
Houston | 1996 | 189171 | 24950 Franz Rd. | Katy | TX | 77493 | 29.8004 | -95.833 | 2026-10-19 | Road only (Franz Rd) - approx.
Houston | 10671 | 190024 | 10420 Fm 1464 | Richmond | TX | 77407 | 29.662 | -95.6869 | 2026-10-19 | OSM CVS store match
Houston | 10637 | 190025 | 6750 Reading Road | Rosenberg | TX | 77471 | 29.5405 | -95.7519 | 2026-10-19 | Census address match
Houston | 5839 | 189419 | 8960 Barker Cypress Rd. | Cypress | TX | 77433 | 29.9077 | -95.6859 | 2026-10-26 | Census address match
Houston | 5884 | 189421 | 12260 Bellaire Blvd. | Houston | TX | 77072 | 29.7037 | -95.5958 | 2026-10-26 | Census address match
Houston | 7805 | 189523 | 5757 New Territory Blvd | Sugar Land | TX | 77479 | 29.5909 | -95.6771 | 2026-10-26 | OSM CVS store match
Houston | 3693 | 189279 | 7950 S. Gessner Rd. | Houston | TX | 77036 | 29.6916 | -95.5356 | 2026-11-02 | Census address match
Houston | 4474 | 189322 | 2781 Dulles Ave. | Missouri City | TX | 77459 | 29.5839 | -95.5806 | 2026-11-02 | Census address match
Houston | 10664 | 190021 | 2180 Woodforest Parkway N. | Montgomery | TX | 77316 | 30.2815 | -95.5716 | 2026-11-02 | Census address match
Houston | 7448 | 189516 | 815 W. Main St. | Tomball | TX | 77375 | 30.094 | -95.6231 | 2026-11-02 | Census address match
Houston | 7476 | 189519 | 5401 Washington Ave | Houston | TX | 77007 | 29.7705 | -95.4164 | 2026-11-09 | Census address match
Houston | 6655 | 189471 | 1569 11Th St | Huntsville | TX | 77340 | 30.7184 | -95.5684 | 2026-11-09 | Road only (11th St) - approx.
Houston | 10177 | 189927 | 2720 Fm 1463 | Katy | TX | 77494 | 29.7521 | -95.8517 | 2026-11-09 | Census address match
Houston | 5972 | 189424 | 5305 Avenue I | Rosenberg | TX | 77471 | 29.5582 | -95.7733 | 2026-11-09 | Census address match
Houston | 10350 | 189979 | 4523 L J Parkway | Sugar Land | TX | 77479 | 29.5462 | -95.5845 | 2026-11-09 | Census address match
Houston | 7475 | 189521 | 1350 Kingwood Dr | Kingwood | TX | 77339 | 30.0493 | -95.2358 | 2026-11-16 | Census address match
Houston | 5519 | 189423 | 1295 East League City Pkwy. | League City | TX | 77573 | 29.5177 | -95.024 | 2026-11-16 | Road only (E League City Pkwy) - approx.
Houston | 11067 | 190022 | 2735 Sienna Parkway | Missouri City | TX | 77459 | 29.4849 | -95.5215 | 2026-11-16 | Census address match
Houston | 10544 | 189980 | 5902 Fm 1463 Rd. | Katy | TX | 77494 | 29.7063 | -95.8461 | 2026-11-30 | Census address match
Houston | 10604 | 190023 | 4489 County Road 94 | Manvel | TX | 77578 | 29.5314 | -95.3835 | 2026-11-30 | Census address match
Houston | 6000 | 189420 | 4101 Fairmont Pkwy., | Pasadena | TX | 77504 | 29.651 | -95.1831 | 2026-11-30 | Census address match
Houston | 7120 | 189522 | 11600 Shadow Creek Pkwy. | Pearland | TX | 77584 | 29.5795 | -95.3962 | 2026-11-30 | Census address match
Austin / Central | 6893 | 189469 | 3569 Far West Blvd. | Austin | TX | 78731 | 30.3537 | -97.7541 | 2026-10-12 | Census address match
Austin / Central | 10691 | 190027 | 302 Gateway North | Marble Falls | TX | 78654 | 30.563 | -98.2744 | 2026-10-12 | Census address match
Austin / Central | 10875 | 190026 | 3000 Rm 1431 | Round Rock | TX | 78681 | 30.5507 | -97.7394 | 2026-10-19 | OSM CVS store match - verify (3000 Sendero Springs Dr)
Austin / Central | 1430 | 189074 | 2101 S. Lamar Blvd., Unit B | Austin | TX | 78704 | 30.2483 | -97.77 | 2026-10-26 | Census address match
Austin / Central | 6822 | 189470 | 5256 Burnet Rd Ste B | Austin | TX | 78756 | 30.3259 | -97.7397 | 2026-10-26 | Census address match
Austin / Central | 5776 | 189425 | 105 Wonderworld Drive | San Marcos | TX | 78666 | 29.8655 | -97.9631 | 2026-10-26 | Census address match
Austin / Central | 10221 | 189928 | 2502 Trimmier Rd. | Killeen | TX | 76542 | 31.0938 | -97.7326 | 2026-11-16 | Census address match
Austin / Central | 10585 | 189982 | 3300 W. Stan Schlueter Loop | Killeen | TX | 76549 | 31.0853 | -97.7844 | 2026-11-16 | Census address match
Austin / Central | 357 | 188921 | 1701 E. Parmer Ln. | Austin | TX | 78754 | 30.3868 | -97.6485 | 2026-11-30 | Census address match
Austin / Central | 928 | 189024 | 800 West Old Settlers Blvd | Round Rock | TX | 78681 | 30.5361 | -97.6951 | 2026-11-30 | Census address match
San Antonio | 10633 | 190030 | 3502 Se Military Dr. | San Antonio | TX | 78223 | 29.3531 | -98.4265 | 2026-10-12 | Census address match
San Antonio | 10947 | 190028 | 1910 State Highway 46 W | New Braunfels | TX | 78132 | 29.6715 | -98.0563 | 2026-10-19 | Census address match
San Antonio | 10750 | 190029 | 9050 Fm 1560 N | San Antonio | TX | 78254 | 29.5242 | -98.718 | 2026-10-19 | Census address match
San Antonio | 10595 | 189984 | 200 Cibolo Valley Dr. | Cibolo | TX | 78108 | 29.6084 | -98.2661 | 2026-11-02 | Road only (Cibolo Valley Dr) - approx.
San Antonio | 7307 | 189526 | 2018 Culebra Rd. | San Antonio | TX | 78201 | 29.4465 | -98.5397 | 2026-11-02 | Census address match
San Antonio | 10579 | 189983 | 4600 Broadway St. | Alamo Heights | TX | 78209 | 29.4683 | -98.4636 | 2026-11-16 | Census address match
San Antonio | 7808 | 189524 | 4805 Medical Dr | San Antonio | TX | 78229 | 29.5104 | -98.5803 | 2026-11-30 | Census address match
San Antonio | 7784 | 189525 | 110 S King St | Seguin | TX | 78155 | 29.5687 | -97.9499 | 2026-11-30 | Census address match
South TX | 5651 | 189422 | 1602 East Highway 83 | Weslaco | TX | 78596 | 26.1559 | -97.974 | 2026-10-26 | OSM CVS store match - verify (1602 E 6th St)
South TX | 10405 | 189978 | 103 W. Monte Cristo Rd. | Edinburg | TX | 78541 | 26.3406 | -98.1799 | 2026-11-02 | Road only (W Monte Cristo Rd) - approx.
South TX | 10107 | 189926 | 2300 N Conway Ave. | Mission | TX | 78574 | 26.2302 | -98.3227 | 2026-11-02 | OSM CVS store match
South TX | 248 | 188919 | 2121 W. Trenton Rd. | Edinburg | TX | 78539 | 26.2647 | -98.1921 | 2026-11-09 | Census address match
South TX | 2328 | 189190 | 3205 S. Alameda St. | Corpus Christi | TX | 78404 | 27.7564 | -97.3898 | 2026-11-16 | OSM address match
Outlier | 10594 | 189977 | 500 N. Carrollton Ave. | New Orleans | LA | 70119 | 29.9775 | -90.0972 | 2026-10-26 | Census address match
Outlier | 1543 | 189116 | 7301 Hillside Rd. | Amarillo | TX | 79119 | 35.1467 | -101.9201 | 2026-11-30 | Census address match

## Open Items
Open items to close before the plan is final
Item | Detail | Owner
Ship-from point / vendor lead time | Transit days on Assumptions are placeholders. Need the vendor ship point and production lead time. | Owner: Procurement / vendor
Meaning and firmness of MSD | Plan treats MSD as the install window opening and CSD (MSD + 7) as the deadline. Confirm with CVS/program manager. | Owner: PM
Unit configs for stores not validated | 30 stores show Not Validated Yet and have no unit config. Plan uses the default and flags them; PO quantities should not be locked until configs are confirmed. | Owner: CVS / layout validation
Labor model TBD | MV vs Store Labor is blank for the not-validated stores and some validated stores (hours 0). Affects who receives/installs. | Owner: PM
Remote stores | Amarillo (1543) and New Orleans (10594) are far from any cluster; decide on dedicated delivery or bundling with another run. | Owner: Logistics
Receiving windows / store contacts | Need site delivery hours, dock/no-dock, and receiving contacts per store, particularly for freestanding pads and convenience store types. | Owner: Field ops
Crew plan | Region Summary gives peak-week load; confirm self-perform vs sub and travel/lodging for South TX and outliers. | Owner: COO / Ops
Tie to PO | Once configs firm up, roll units per region into the vendor PO and delivery schedule. | Owner: Procurement