## Current List
CS# | Store # | 5 Digit Store | Div | Reg | Dist | Cluster | Address | City | State | Zip | Store Type | PM/SPM | Layout Validation Status | MV or Store Labor? | Merchandising Hours | GC | MV | Unit Configuration | MSD | CSD | Notes
190032 | 10880 | 10880 | 07 | 37 | 03 | 149 | 8580 N. MACARTHUR BLVD | IRVING | TX | 75063 | Freestanding | Soto; Joseph | Approved | MV | 64 | Core CMCI | Channel Partners | 3 | 2026-10-05
190020 | 10996 | 10996 | 07 | 33 | 01 | 145 | 9663 W. FM 1097 RD. | WILLIS | TX | 77318 | Freestanding | Cathey; Chris C. | Approved | MV | 32 | Core CMCI | Pivotal | 3 | 2026-10-12
189469 | 6893 | 06893 | 07 | 35 | 02 | 147 | 3569 FAR WEST BLVD. | AUSTIN | TX | 78731 | Strip Shopping Center | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-12
190027 | 10691 | 10691 | 07 | 35 | 01 | 147 | 302 GATEWAY NORTH | MARBLE FALLS | TX | 78654 | Freestanding | Soto; Joseph | Approved | MV | 44 | Core CMCI | Merchco | 3 | 2026-10-12
190030 | 10633 | 10633 | 07 | 35 | 04 | 148 | 3502 SE MILITARY DR. | SAN ANTONIO | TX | 78223 | Freestanding | Soto; Joseph | Approved | MV | 6 | Core CMCI | Pivotal | 3 | 2026-10-12
189985 | 10324 | 10324 | 07 | 36 | 05 | 149 | 6420 GASTON AVE. | DALLAS | TX | 75214 | Convenience | Soto; Joseph | Approved | Store Labor | 22 | Core CMCI | N/A | 4 | 2026-10-12
190033 | 10642 | 10642 | 07 | 37 | 05 | 149 | 1101 FM 2181 | CORINTH | TX | 76210 | Freestanding | Soto; Joseph | Approved | MV | 34 | Core CMCI | Channel Partners | 3 | 2026-10-12
189518 | 7092 | 07092 | 07 | 33 | 02 | 145 | 110 W. 20TH ST. | HOUSTON | TX | 77008 | Freestanding | Cathey; Chris C. | Approved | MV | 70 | Core CMCI | Pivotal | 3 | 2026-10-19
189171 | 1996 | 01996 | 07 | 34 | 01 | 146 | 24950 FRANZ RD. | KATY | TX | 77493 | Freestanding | Soto; Joseph | Approved | Store Labor | 38 | Core CMCI | N/A | 3 | 2026-10-19
190024 | 10671 | 10671 | 07 | 34 | 04 | 146 | 10420 FM 1464 | RICHMOND | TX | 77407 | Freestanding | Soto; Joseph | Approved | Store Labor | 8 | Core CMCI | N/A | 3 | 2026-10-19
190025 | 10637 | 10637 | 07 | 34 | 04 | 147 | 6750 READING ROAD | ROSENBERG | TX | 77471 | Freestanding | Soto; Joseph | Approved | Store Labor | 14 | Core CMCI | N/A | 3 | 2026-10-19
190026 | 10875 | 10875 | 07 | 35 | 01 | 147 | 3000 RM 1431 | ROUND ROCK | TX | 78681 | Freestanding | Soto; Joseph | Approved | Store Labor | 10 | Core CMCI | N/A | 3 | 2026-10-19
190029 | 10750 | 10750 | 07 | 35 | 04 | 148 | 9050 FM 1560 N | SAN ANTONIO | TX | 78254 | Freestanding | Soto; Joseph | Approved | MV | 40 | Core CMCI | Pivotal | 3 | 2026-10-19
190028 | 10947 | 10947 | 07 | 35 | 03 | 148 | 1910 STATE HIGHWAY 46 W | NEW BRAUNFELS | TX | 78132 | Freestanding | Soto; Joseph | Approved | Store Labor | 6 | Core CMCI | N/A | 3 | 2026-10-19
189620 | 8345 | 08345 | 07 | 37 | 02 | 149 | 5195 LAKE RIDGE PKWY. | GRAND PRAIRIE | TX | 75052 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 2 - Right Hinge | 2026-10-19
189473 | 6865 | 06865 | 07 | 37 | 03 | 149 | 1099 W. MAIN ST | LEWISVILLE | TX | 75067 | Freestanding | Soto; Joseph | Approved | MV | 52 | Core CMCI | Channel Partners | 4 | 2026-10-19
189419 | 5839 | 05839 | 07 | 33 | 01 | 145 | 8960 BARKER CYPRESS RD. | CYPRESS | TX | 77433 | Freestanding | Cathey; Chris C. | Approved | MV | 10 | Core CMCI | Pivotal | 3 | 2026-10-26
189977 | 10594 | 10594 | 07 | 32 | 03 | 145 | 500 N. CARROLLTON AVE. | NEW ORLEANS | LA | 70119 | Freestanding | Cathey; Chris C. | Approved | Store Labor | 34 | Core CMCI | N/A | 3 | 2026-10-26
189422 | 5651 | 05651 | 07 | 34 | 02 | 146 | 1602 EAST HIGHWAY 83 | WESLACO | TX | 78596 | Freestanding | Soto; Joseph | Approved | MV | 52 | Core CMCI | Merchco | 4 | 2026-10-26
189421 | 5884 | 05884 | 07 | 34 | 01 | 146 | 12260 BELLAIRE BLVD. | HOUSTON | TX | 77072 | Freestanding | Soto; Joseph | Approved | Store Labor | 30 | Core CMCI | N/A | 3 | 2026-10-26
189523 | 7805 | 07805 | 07 | 34 | 04 | 147 | 5757 NEW TERRITORY BLVD | SUGAR LAND | TX | 77479 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-26
189425 | 5776 | 05776 | 07 | 35 | 02 | 147 | 105 WONDERWORLD DRIVE | SAN MARCOS | TX | 78666 | Freestanding Pad | Soto; Joseph | Approved | MV | 74 | Core CMCI | Merchco | 3 | 2026-10-26
189074 | 1430 | 01430 | 07 | 35 | 02 | 148 | 2101 S. LAMAR BLVD., UNIT B | AUSTIN | TX | 78704 | Strip Shopping Center | Soto; Joseph | Approved | MV | 40 | Core CMCI | Pivotal | 3 | 2026-10-26
189470 | 6822 | 06822 | 07 | 35 | 02 | 148 | 5256 BURNET RD STE B | AUSTIN | TX | 78756 | Freestanding | Soto; Joseph | Approved | Store Labor | 12 | Core CMCI | N/A | 3 | 2026-10-26
189281 | 3187 | 03187 | 07 | 37 | 03 | 149 | 1000 E. SANDY LAKE RD. | COPPELL | TX | 75019 | Freestanding Pad | Soto; Joseph | Approved | MV | 46 | Core CMCI | Channel Partners | 3 | 2026-10-26
189528 | 7787 | 07787 | 07 | 37 | 03 | 149 | 2220 CROSS TIMBERS RD | FLOWER MOUND | TX | 75028 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-10-26
189516 | 7448 | 07448 | 07 | 33 | 01 | 145 | 815 W. MAIN ST. | TOMBALL | TX | 77375 | Freestanding | Cathey; Chris C. | Approved | MV | 36 | Core CMCI | Pivotal | 3 | 2026-11-02
190021 | 10664 | 10664 | 07 | 33 | 01 | 145 | 2180 WOODFOREST PARKWAY N. | MONTGOMERY | TX | 77316 | Freestanding Pad | Cathey; Chris C. | Approved | Store Labor | 34 | Core CMCI | N/A | 3 | 2026-11-02
189926 | 10107 | 10107 | 07 | 34 | 02 | 146 | 2300 N CONWAY AVE. | MISSION | TX | 78574 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-02
189978 | 10405 | 10405 | 07 | 34 | 02 | 146 | 103 W. MONTE CRISTO RD. | EDINBURG | TX | 78541 | Freestanding | Soto; Joseph | Approved | MV | 62 | Core CMCI | Merchco | 4 | 2026-11-02
189279 | 3693 | 03693 | 07 | 34 | 04 | 147 | 7950 S. GESSNER RD. | HOUSTON | TX | 77036 | Freestanding | Soto; Joseph | Approved | MV | 56 | Core CMCI | Merchco | 3 | 2026-11-02
189322 | 4474 | 04474 | 07 | 34 | 04 | 147 | 2781 DULLES AVE. | MISSOURI CITY | TX | 77459 | Freestanding | Soto; Joseph | Approved | MV | 66 | Core CMCI | Merchco | 3 | 2026-11-02
189984 | 10595 | 10595 | 07 | 35 | 03 | 148 | 200 CIBOLO VALLEY DR. | CIBOLO | TX | 78108 | Freestanding | Soto; Joseph | Approved | Store Labor | 36 | Core CMCI | N/A | 4 | 2026-11-02
189526 | 7307 | 07307 | 07 | 35 | 04 | 148 | 2018 CULEBRA RD. | SAN ANTONIO | TX | 78201 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-02
189474 | 6960 | 06960 | 07 | 37 | 04 | 149 | 2142 N JOSEY LN | CARROLLTON | TX | 75006 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-11-02
189529 | 7804 | 07804 | 07 | 37 | 04 | 149 | 6401 W PARKER RD | PLANO | TX | 75093 | Freestanding | Soto; Joseph | Approved | N/A | 0 | Core CMCI | N/A | 3 | 2026-11-02
189519 | 7476 | 07476 | 07 | 33 | 02 | 145 | 5401 WASHINGTON AVE | HOUSTON | TX | 77007 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-09
188919 | 248 | 00248 | 07 | 34 | 02 | 146 | 2121 W. TRENTON RD. | EDINBURG | TX | 78539 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189979 | 10350 | 10350 | 07 | 34 | 03 | 146 | 4523 L J PARKWAY | SUGAR LAND | TX | 77479 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189927 | 10177 | 10177 | 07 | 34 | 04 | 147 | 2720 FM 1463 | KATY | TX | 77494 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
189424 | 5972 | 05972 | 07 | 34 | 04 | 147 | 5305 AVENUE I | ROSENBERG | TX | 77471 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-09
190031 | 10635 | 10635 | 07 | 36 | 01 | 148 | 476 W. 1-30 | ROYSE CITY | TX | 75189 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-09
189471 | 6655 | 06655 | 07 | 36 | 03 | 148 | 1569 11TH ST | HUNTSVILLE | TX | 77340 | Freestanding | Soto; Joseph | Approved | MV | 56 | Core CMCI | Pivotal | 3 | 2026-11-09
189426 | 5799 | 05799 | 07 | 37 | 05 | 149 | 6301 EL DORADO PKWY. | MCKINNEY | TX | 75070 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-09
189986 | 10271 | 10271 | 07 | 37 | 05 | 149 | 1510 W. HICKORY ST. | DENTON | TX | 76201 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-09
189521 | 7475 | 07475 | 07 | 33 | 03 | 145 | 1350 KINGWOOD DR | KINGWOOD | TX | 77339 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
190022 | 11067 | 11067 | 07 | 33 | 04 | 145 | 2735 SIENNA PARKWAY | MISSOURI CITY | TX | 77459 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
189190 | 2328 | 02328 | 07 | 34 | 03 | 146 | 3205 S. ALAMEDA ST. | CORPUS CHRISTI | TX | 78404 | Freestanding Pad | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189423 | 5519 | 05519 | 07 | 34 | 03 | 146 | 1295 EAST LEAGUE CITY PKWY. | LEAGUE CITY | TX | 77573 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189982 | 10585 | 10585 | 07 | 35 | 01 | 147 | 3300 W. STAN SCHLUETER LOOP | KILLEEN | TX | 76549 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189928 | 10221 | 10221 | 07 | 35 | 01 | 147 | 2502 TRIMMIER RD. | KILLEEN | TX | 76542 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-16
189983 | 10579 | 10579 | 07 | 35 | 03 | 148 | 4600 BROADWAY ST. | ALAMO HEIGHTS | TX | 78209 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-16
189472 | 6965 | 06965 | 07 | 36 | 04 | 148 | 7203 SKILLMAN ST. | DALLAS | TX | 75231 | Freestanding Pad | Soto; Joseph | Not Validated Yet | MV |  | Core CMCI | Pivotal |  | 2026-11-16
189987 | 10523 | 10523 | 07 | 37 | 05 | 149 | 270 STONEBROOK PKWY. | FRISCO | TX | 75036 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-16
189427 | 5952 | 05952 | 07 | 37 | 05 | 149 | 2313 W. UNIVERSITY AVE. | MCKINNEY | TX | 75071 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-16
189522 | 7120 | 07120 | 07 | 33 | 04 | 145 | 11600 SHADOW CREEK PKWY. | PEARLAND | TX | 77584 | Freestanding Pad | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189420 | 6000 | 06000 | 07 | 33 | 04 | 145 | 4101 FAIRMONT PKWY., | PASADENA | TX | 77504 | Freestanding | Cathey; Chris C. | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189980 | 10544 | 10544 | 07 | 34 | 04 | 146 | 5902 FM 1463 RD. | KATY | TX | 77494 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
190023 | 10604 | 10604 | 07 | 33 | 04 | 146 | 4489 COUNTY ROAD 94 | MANVEL | TX | 77578 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
189024 | 928 | 00928 | 07 | 35 | 01 | 147 | 800 WEST OLD SETTLERS BLVD | ROUND ROCK | TX | 78681 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
188921 | 357 | 00357 | 07 | 35 | 01 | 147 | 1701 E. PARMER LN. | AUSTIN | TX | 78754 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Merchco |  | 2026-11-30
189524 | 7808 | 07808 | 07 | 35 | 03 | 148 | 4805 MEDICAL DR | SAN ANTONIO | TX | 78229 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189525 | 7784 | 07784 | 07 | 35 | 03 | 148 | 110 S KING ST | SEGUIN | TX | 78155 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Pivotal |  | 2026-11-30
189530 | 7562 | 07562 | 07 | 37 | 05 | 149 | 9075 LEGACY DR. | FRISCO | TX | 75033 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-30
189116 | 1543 | 01543 | 07 | 38 | 01 | 149 | 7301 HILLSIDE RD. | AMARILLO | TX | 79119 | Freestanding | Soto; Joseph | Not Validated Yet |  |  | Core CMCI | Channel Partners |  | 2026-11-30

## Rejected Candidates
Store # | 5 Digit Store | CS# | Div | Reg | Dist | Cluster | Address | City | State | Zip | Store Type | PM/SPM | Layout Validation Status | MV or Store Labor? | Merchandising Hours | Unit Configuration | MSD | CSD
9481 | 09481 | 189774 | 09 | 89 | 02 | 169 | 12444 BEACH BOULEVARD | STANTON | CA | 90680 | Freestanding | Winkler; Jacob S | Rejected |  |  |  | 2026-11-09
915 | 00915 | 188989 | 01 | 02 | 03 | 105 | 19 DODGE ST. | BEVERLY | MA | 01915 | Freestanding Pad | Wheeler; Nicolas | Rejected |  |  |  | 2026-10-05
224 | 00224 | 188874 | 01 | 02 | 03 | 105 | 650 MAIN STREET | READING | MA | 01867 | Downtown | Wheeler; Nicolas | Rejected |  |  |  | 2026-10-19
860 | 00860 | 188992 | 01 | 03 | 02 | 106 | 6 POST OFFICE SQ | HARWICHPORT | MA | 02646 | Convenience | Wheeler; Nicolas | Rejected |  |  |  | 2026-11-30
1213 | 01213 | 189038 | 01 | 04 | 03 | 109 | 94 PARK STREET | NEW CANAAN | CT | 06840 | Downtown | Charlotinambrose; Mildred | Rejected |  |  |  | 2026-11-09
11060 | 11060 | 190007 | 02 | 06 | 05 | 115 | 1-50 50TH AVE | LONG ISLAND CITY | NY | 11101 | Downtown | Kaegi; Jacqueline | Rejected |  |  |  | 2026-11-30
1833 | 01833 | 189103 | 02 | 17 | 02 | 120 | 4238 WILSON BLVD/BALLSTON COMMONS #1831 | ARLINGTON | VA | 22203 | Regional Mall | Meath; Lori A. | Rejected |  |  |  | 2026-10-19
8088 | 08088 | 189571 | 03 | 58 | 02 | 130 | 2100 W. STADIUM BLVD. | ANN ARBOR | MI | 48103 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
1389 | 01389 | 189072 | 04 | 19 | 02 | 140 | 2912 CHAIN BRIDGE ROAD | OAKTON | VA | 22124 | Strip Shopping Center | Meath; Lori A. | Rejected |  |  |  | 2026-10-12
3705 | 03705 | 189277 | 05 | 83 | 03 | 144 | 10701 NW 41ST ST | DORAL | FL | 33178 | Freestanding | townsend; kevin | Rejected |  |  |  | 2026-11-30
5443 | 05443 | 189374 | 07 | 32 | 02 | 145 | 1920 KALISTE SALOOM | LAFAYETTE | LA | 70508 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
7435 | 07435 | 189520 | 07 | 33 | 03 | 145 | 23865 FM 1314 RD. | PORTER | TX | 77365 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-11-09
9108 | 09108 | 189671 | 09 | 87 | 04 | 165 | 1655 S. CENTRE CITY PKWY. | ESCONDIDO | CA | 92025 | Freestanding Pad | Foster; Ryan | Rejected |  |  |  | 2026-10-26
9614 | 09614 | 189791 | 09 | 90 | 02 | 172 | 1122 EAST BROADWAY | GLENDALE | CA | 91205 | Convenience | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
9787 | 09787 | 189839 | 09 | 90 | 02 | 172 | 3943 SAN FERNANDO RD. | GLENDALE | CA | 91204 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-26
2981 | 02981 | 189240 | 12 | 61 | 04 | 183 | 1201 N. STATE ST. | CHICAGO | IL | 60610 | Freestanding | O Rourke; Jessica A | Rejected |  |  |  | 2026-11-16
2054 | 02054 | 189131 | 01 | 03 | 04 | 107 | 136 NAHATAN ST. | NORWOOD | MA | 02062 | Strip Shopping Center | Manning; Robert | Rejected |  |  |  | 2026-10-26
300 | 00300 | 188892 | 02 | 06 | 01 | 113 | 725 SAW MILL RIVER RD, ARDSLEY S/C | ARDSLEY | NY | 10502 | Convenience | Kaegi; Jacqueline | Rejected |  |  |  | 2026-10-19
1231 | 01231 | 189043 | 02 | 06 | 01 | 113 | 807 WHITE PLAINS RD. | SCARSDALE | NY | 10583 | Freestanding | Kaegi; Jacqueline | Rejected |  |  |  | 2026-10-26
2225 | 02225 | 189142 | 02 | 08 | 01 | 115 | 232 SMITHTOWN BOULEVARD | NESCONSET | NY | 11767 | Freestanding Pad | Kaegi; Jacqueline | Rejected |  |  |  | 2026-11-02
4323 | 04323 | 189312 | 03 | 31 | 01 | 127 | 10050 WOODLAND RD. | LENEXA | KS | 66220 | Freestanding Pad | O Rourke; Jessica A | Rejected |  |  |  | 2026-10-26
7859 | 07859 | 189588 | 08 | 30 | 04 | 151 | 6370 N. CAMPBELL AVE., #120 | TUCSON | AZ | 85718 | Convenience | Sotelo; Rolly | Rejected |  |  |  | 2026-11-30
9498 | 09498 | 189756 | 09 | 52 | 01 | 157 | 1800 SARATOGA AVE. | SAN JOSE | CA | 95129 | Freestanding Pad | Morgan; Marina L | Rejected |  |  |  | 2026-10-26
7774 | 07774 | 189535 | 09 | 52 | 01 | 157 | 850 CALIFORNIA ST | MOUNTAIN VIEW | CA | 94041 | Downtown | Morgan; Marina L | Rejected |  |  |  | 2026-10-26
9148 | 09148 | 189668 | 09 | 87 | 03 | 164 | 313 WASHINGTON ST. | SAN DIEGO | CA | 92103 | Freestanding | Foster; Ryan | Rejected |  |  |  | 2026-11-02
9591 | 09591 | 189768 | 09 | 88 | 01 | 166 | 30842 S PACIFIC COAST | LAGUNA BEACH | CA | 92651 | Strip Shopping Center | Fitzpatrick; John T | Rejected |  |  |  | 2026-10-26
8837 | 08837 | 189638 | 09 | 90 | 03 | 173 | 222 N. MARKET ST. | INGLEWOOD | CA | 90301 | Freestanding | Cathey; Chris C. | Rejected |  |  |  | 2026-10-19
9698 | 09698 | 189824 | 09 | 88 | 02 | 168 | 100 W. FOOTHILL BLVD. | UPLAND | CA | 91786 | Freestanding Pad | Winkler; Jacob S | Rejected |  |  |  | 2026-10-05
8895 | 08895 | 189691 | 09 | 88 | 02 | 170 | 775 E. FOOTHILL BOULEVARD | POMONA | CA | 91767 | Strip Shopping Center | Winkler; Jacob S | Rejected |  |  |  | 2026-11-16
189064 | 1315 | 01315 | 04 | 14 | 04 | 138 | 1101 SOUTHWEST END BLVD. | QUAKERTOWN | PA | 18951 | Freestanding | Santalucia; Dawn | Rejected |  |  |  | 2026-10-26
189566 | 8016 | 08016 | 03 | 57 | 05 | 129 | 40925 GARFIELD ROAD | CLINTON TOWNSHIP | MI | 48038 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
189572 | 8089 | 08089 | 03 | 58 | 02 | 130 | 935 S. MAIN ST. | CHELSEA | MI | 48118 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-02
189073 | 1411 | 01411 | 04 | 19 | 02 | 140 | 8124 ARLINGTON BLVD, YORKTOWN CTR | FALLS CHURCH | VA | 22042 | Strip Shopping Center | Meath; Lori A. | Rejected |  |  |  | 2026-11-02
189198 | 3154 | 03154 | 01 | 05 | 01 | 110 | 59 MAIN STREET | WARWICK | NY | 10990 | Freestanding | Messer; Laura R | Rejected |  |  |  | 2026-11-09
189041 | 1414 | 01414 | 01 | 07 | 01 | 112 | 1195 OAKLAWN AVENUE | CRANSTON | RI | 02920 | Freestanding Pad | Messer; Laura R | Rejected |  |  |  | 2026-11-09
189573 | 8216 | 08216 | 03 | 58 | 02 | 130 | 1700 SOUTH INDUSTRIAL HIGHWAY | ANN ARBOR | MI | 48104 | Freestanding | Clark; Josh D. | Rejected |  |  |  | 2026-11-09
189268 | 3218 | 03218 | 05 | 41 | 01 | 142 | 10200 SEMINOLE BLVD | SEMINOLE | FL | 33778 | Freestanding | townsend; kevin | Rejected |  |  |  | 2026-11-09
189625 | 8420 | 08420 | 08 | 30 | 04 | 151 | 7740 N CORTARO RD | TUCSON | AZ | 85743 | Freestanding | Sotelo; Rolly | Rejected |  |  |  | 2026-11-09
189406 | 5741 | 05741 | 03 | 58 | 01 | 129 | 7488 VILLAGE CENTER DR. | WHITMORE LAKE | MI | 48189 | Freestanding Pad | Clark; Josh D. | Rejected |  |  |  | 2026-11-30
188962 | 660 | 00660 | 04 | 13 | 01 | 135 | 9875 BUSTLETON AVENUE | PHILADELPHIA | PA | 19115 | Freestanding Pad | Santalucia; Dawn | Rejected |  |  |  | 2026-10-26
189840 | 9784 | 09784 | 09 | 90 | 02 | 172 | 1030 COLORADO BLVD. | EAGLE ROCK | CA | 90041 | Freestanding | Cathey; Chris C. | Approved | MV | 60 | 2 | 2026-10-19